## Sheet1
Testcase Id | Module Name | Test Casse | Pre Condition | Step to Execute | Test Data | Expected Result | Actual Result |  | Priority | Severity | Files | Remark | Resolved or Not
BG_01 | User Login | Try to log in as new user | New user already added with valid credentials User should be on login page | 1. Enter valid credential in Email and Password textfield 2. Click on Login Button 3. Check the outcome | Emaqil : nalapo4274@aganseo.com Pass: 123456 | User should be login successfully and redirect to dashboard | User unable to login System display mail is not register | PASS | High | High | https://drive.google.com/file/d/1qiaqcI2BdZF4oT9CWldTHk1BYn2rP1-k/view?usp=sharing | User should be login easily if mail and password are correct | Not a Bug — Test used invalid/unregistered credentials; role-deactivation login messaging already correct on this build
Bg_02 | Create Invoice | Try to create invoice where category is not selected only amount entered | User should be on the invoice page Client should already added | 1. Click on add Invoice label button 2. Select client from selection list 3. Enter all required detail 4. In one service section donot select service and enter any thing only enter amount 5. Click on Save button |  | Invoice should not added Error message toast select any category | Invoice added successfully. And category display blank | FAIL | Low | Medium | https://drive.google.com/file/d/1SqfQBws3cSj3sDfU5plNxF6uOOWCsLK_/view?usp=drive_link | See here user will always select category than enter amouny but still make category mandatory so user have to choose any one | Resolved — Category is now required for any invoice line with a description/amount (lib/validators.ts, InvoiceForm.tsx)
Bg_03 | Edit Invoice | Try to edit the invoice | User should be on the invoice page Invoice already added | 1. Locate Invoice in list and Click on edit button next to it 2. Check is it redirect user any where or not |  | Edit Invoice form should be opened with prefilled data of the invoice | Nothing will happen edit button not worked | FAIL | High | High | https://drive.google.com/file/d/1LQgmI7QR3WXRkDl8eL2aSujDoDkr4zld/view?usp=drive_link | Edit button should be work properly . See the video from last not from starting | Resolved — Verified live: Edit navigates & loads correctly; was dev-mode compile delay (~2-6s), not a real failure. Root cause was Bg_05's wrong heading, now fixed
Bg_04 | Delete | Try to delete invoice | User should be on the invoice page Invoice already added | 1. Locate Invoice in list and Click on Delete button next to it 2. Check popup box and clcik on confirm button 3. And check the invoice list is the invoice delete or not |  | Invoice is deleted successfully | Invoice deleted successfully But the confirm popup box appear is chrome bydefault instead of custom properly | FAIL | low | low | https://drive.google.com/file/d/103JSRtxCp1SR7hk55zzoNU3hZRcxdqRX/view?usp=sharing | Confrim popup box should be made custom for website instead of Chrome bydefault it make bad immpression to client | Resolved — Native confirm() replaced with themed ConfirmModal across Invoices/Clients/Payments/Groups/Roles
Bg_05 | Edit Invoice | verify Ui of edit Invoice page | User should be on the Edit invoice page | 1. Verify all the data prefilled properly or not 2. Check the static data are placed properly or not 3. Verify any data or text overlapped on each other or not |  | Edit section should be display properly All the form saved data would be filled in all the section propelry UI should be display perfect | Add Invoice display instead of Update or Edit Invoice in label | FAIL | low | low | https://drive.google.com/file/d/1_002b5_WbtK1Eie0WIBaLRR29ETnIpfb/view?usp=sharing | See the main heading should be display from so user can't get confuse in Add invoice and update Invoice | Resolved — Edit Invoice page now shows "Edit Invoice" instead of "Add Invoice"
Bg_06 | Client | Try to delete Client contain invoice or payment | User should be on the client section Client should be already added Paymnet or Invoice already added of his name in list | 1. Click on the delte button next to the client name 2. Confirm the deletion on clicking confirm button 3. And check the outcome |  | Clinet should not get deleted Error message should dispay Invoice/payment is belongs to the clinet can't get deleted | Here client got deleted all the invoice and payment belongs to client are labeled as Unknown | FAIL | High | High | https://drive.google.com/file/d/1EO6iASfibuiZJl3PkMa1jGSEGB24lQvF/view?usp=drive_link | Cleint should get delete only when it contain zero invoice and paymnet onit Otherwise disable the delete button for it | Resolved — Deleting a client with existing invoices/payments is now blocked (409) both server-side and via a disabled Delete button
Bg_07 | List handling | Check how the list is handled in all the section | 10+ data should be entered in all the list | 1. Go to each section and see is the data is seprated or handled by pagination method or not and is there any filter or search bar present in it |  | Search bar should be there and other filter should present there And for handled huge data pagination should be present in it | No filter searchbar and pagination system present in the all section | Improvement | Medium | Medium | https://drive.google.com/file/d/1ECAjZHp34oqJTMDe4YtwuBukp1g0ycvj/view?usp=drive_link | Searchbar should be presernt in the list aswell as filter And data should be manage in Pagination so that it not face problem in loading | Resolved — Search bar, filter dropdowns (status/mode/group), and pagination (10/25/50 rows) now implemented across Invoices, Clients, Payments, Groups, Users, and the Outstanding/Received report tabs
Bg_08 | Bill pdf | Verify all the data present in the Invoice's pdf matches the actual data or not | Bill should be created and Pdf is already genrated | 1. Check the Service category and discription are proper or not 2. Check the Service amount and total amount on the bill 3. Verify Client Information 4. Verify the firm detail properly all address and bank detail 5. Check terms and condition proiperly displayed or not |  | All the detail should be display and readable properly and the Amount and calculation is also done perfect | Here all calculation and other thing display perfect but Terms and Condition is not describe on the bill | FAIL | Medium | Medium | https://drive.google.com/file/d/1zimI6VR-X4Kc3wWWh4KQGj3kY_vxpWlT/view?usp=drive_link | Terms and condition should be stated on the Invoice so the client get acknowledge our rules | Resolved — Terms & Conditions from Settings now printed on the Invoice PDF
Bg_09 | Invoice | Try to add Invoice by user which has only Add Invoice permission | User should be login with his user Id Only add Invoice permission should be granted to user | 1. Go to Invoice section 2. Click on Add Invoice button 3. Check Invoice number 4. Select Client 5. And select category and fill all required detail 5. Create the Invoice |  | All the Invoice part propelry access. User can add the Invoice properly | Here User unable to select Clien and the category Cleint only accessable when user have Client access And Category when user has Category Access | FAIL | High | High | https://drive.google.com/file/d/1CJwWQSeN4y_qe_KQBtl6RTUbsozSiXIE/view?usp=drive_link | User can Add Invoice proplery and also He can Select Client and Category properly In Invoice. Because he has not access to the section only. | Resolved — Added requireAnyPermission(); Client/Category lists now readable by invoices.create/edit or payments.create/edit, not just customers.view/settings.view
Bg_10 | Client | Try to Add/edit client with invalid Phone number | User should be on the client section | 1. Click on the add Client button 2. Fill all required field 3. Enter Alpha numeric and special character in phone number | 6584asdfedw68d4768qwed@@ | System should toast error Enter valid phone number | Syustem allow user to enter it Client added Successfully | FAIL | low | low | https://drive.google.com/file/d/18Hl48hAEW86nS_o0fTBBGxgaT27WtTPG/view?usp=sharing | As the Accountant or Owner will not enter invalid data in it but still validation should be implemented | Resolved — Client mobile number now validated (digits + optional leading +) client-side and server-side
Bg_11 | Invoice Pdf | Preview the Invoice by adding more than 4 Category | User should be on the Invoice page | 1. Click on the Add invoice button 2. Enter valid detail 3. Add multiple category and AMount more than 4 4. Click on Save and print bill button 5.See the UI of the bill all the Item name and category set properly |  | System should arrang the data properly and if data can't manage in One page new page should be added. All the footer data should be visible properly | Here all the item are visible but user digital signature and Bank details got hidden | FAIL | High | High | https://drive.google.com/file/d/1C3S4om-RWcbkR0k11XGNdpNxwB0RqCkQ/view?usp=sharing | Auto matic new page should be added in PDF if data is crossing the page instead of cutting it. and If data is more than multiple page should auto created in it | Resolved — Invoice PDF now paginates: item rows, totals, bank/signature block and Terms & Conditions auto-flow to a new page instead of overflowing
Bg_12 | add Payment in invoice | Try to add payment in direct Invoice | User should be on Invoice section Unpaid/partial paid Invoice should added | 1. Click on the +payment button 2. Check Invoice number and the Client name 3. try to edit it 4. Enter Valid amount in it 5. Save and check is the status change or not |  | Client or Invoice number field should be disbale for user After adding payment If The invoice is Unpaid than it switch to Partial/paid according to amount | 1. Here it is redirect user to payment section 2. Clinet and Invoice id both field accessable | FAIL | Low | Medium | https://drive.google.com/file/d/1nsh-OYKQCjhaNuXlkt5V9rd7oNxWOCD_/view?usp=drive_link | See if user clicking +payment from Invoice section than user should be on Invoice section only popup box should open And both Name and Invoice id field not accessable | Resolved — "+ Payment" on an invoice now opens PaymentModal inline with Client and Invoice locked, instead of navigating to /payments with editable fields
Bg_13 | Forget pass/Signup | Try to do Signup or forget password | User should be on the login page | 1. Locate Forget password link and click 2. And reset password 3. Try to sign in locate the button 4. And proceed further |  | Password should reset successfully And Account should created if user proceed properly | Signup and forget password link is unavilable on the Login page | Need for Confiramtion | Medium | low | https://drive.google.com/file/d/1HQP8iGrOd5ncP0CItd4mAiXq91LKaOgv/view?usp=drive_link | As I know it client project signup is not necessary but atleast forget password should be avilable | By Design — No public self-registration/self-service password reset; accounts are admin-created only (documented project rule)
Bg_14 | Add User | Try to add user with disabled role | User should on User section Atleaast one role should be disabled in rolesection | 1. Clcik on Add user button 2. Enter all required detail with valid credential 3. In role try to select Deactive Role 4. Click on Submit button |  | System will not show disabled role in the list. If avilable than show error | Here User added Successfully User created | FAIL | Low | Low | https://drive.google.com/file/d/1sQXAQ_kO1T2--GBoZ7JQAkUboutQ40UK/view?usp=sharing | As user unable to login if role is disable If disable role is not display here than this problem will not come | Resolved — Inactive roles are no longer selectable when creating/editing a user (filtered client-side, rejected server-side)
Bg_15 | Add User | Add new user | User should on User section Atleaast one role should be created in rolesection | 1. Enter all detail propelry 2. And click on submit button |  | User will created and in user section user name will be display in list | User created successfully But user name text field is missing here | FAIL | low | low | https://drive.google.com/file/d/1vKLn4PLEuXZY3_rFGKvc4Wki5BLesHIg/view?usp=drive_link | User name field should be avilable so it will display on the user profile all the place Showing email is not proper | Resolved — Added a "Name" field to the User model/form/list (previously only email identified a user)
Bg_16 | Password | Try to check password hide toggle button working or not | User should be on login page and add user page | 1. Click on password field enter text 2. Now click on eye icon next to password textfield and check text displayed or not 3. Now go to user section clcik on edit button enter password in the dfield and check |  | Password will display in text on clicking of it | There is not buttonpresent in the login and the add user section to display Password | FAIL | very low | low | https://drive.google.com/file/d/16pyPGjDV-2UDFL97-c2i_fNumR9wYCb8/view?usp=drive_link | I know it is neglejible but what if Client want to fix it | Resolved — Added a show/hide eye-icon toggle to the Login page and Add/Edit User password fields
Bg_17 | Popupbox | Try to Close the popup box without clciking Cancel button or Submit button | User should be on any section Popup box should be open | 1. Enter the data in the poup box try to close the popup box by clciking outside the box 2. Try same thing in other section also 3. Check is the popup box close whe user is editing the popup or adding data in it |  | Popup box should not clock if the data in it edited or added because after closing it data got reset | Here popup box got closed and data got reset | FAIL | Medium | Medium | https://drive.google.com/file/d/1ZYiMvkDU8v1PMuXsMx1i39KPPuGIJHGF/view?usp=drive_link | In following section popup box got closed which is incorrect 1. Client 2. Group 3. Payment 4. Role & Permission 5. User section They have popup box so make like that until person click close button or submit button it should not get closed | Resolved — Clicking the modal backdrop no longer closes it/discards data; only an explicit Cancel/Close/Save button closes a modal now
Bg_18 | Setting | Verify Validation and required field in the Setting section | User should be on the setting section | 1. Empty all the text field and selection field 2. Click on the Sumbit button 3. Check Is system mark any field as mandatory or not 4. Now enter the invalid data format in the text field like email, Phone number and Account number etc 5. Clcik on the Save button |  | If user Click on the Submit button when all fields are empty than alert message should display please fill the text field. If entering invalid data format in the text field alert message or popup message display fill the data in correct format | Here System didnot mark any field as mandatory And also not detect invalid data format in any field | FAIL | low | low | https://drive.google.com/file/d/1IMarAZYmCpJEK7EAL0CmD89AbGdloEtW/view?usp=drive_link | User should atleast set invalid and valid data format so that if user enter correct data format | Resolved — Settings page now validates firm name (required), email/mobile format, account number, IFSC code, and invoice prefix before saving
Bg_19 | Setting | Verify Service Category add fails with duplicate name | User should be on the setting section 2-3 Category already added | 1. Click on text box and Enter duplicate category tha already avilable in list 2. Click on add button 3. Check the outcome |  | System should toast alert message that category is already added | System allow user to enter duplicate category | FAIL | Medium | Medium | https://drive.google.com/file/d/13ayUfZK79kZC28a7__BjVtAUZmPZmhcF/view?usp=drive_link | Category should not allow as duplicate I know user is one and they will not do such mistake but still. | Resolved — Adding a service category now rejects a case-insensitive duplicate with a clear error
Bg_20 | Setting | Try to replace/remove company logo | User should be on the Setting | 1. Try to locate upload logo section 2. Click on replace button 3. And new logo and check preview |  | Logo will be updated and system will se new logo | Here the logo section is not present so user can update or remove the logo | Need for Confiramtion |  |  |  | As there should be a option present so that user can replace his logo with his updated logo if he want | Enhancement — Needs Product Confirmation; logo upload/replace is a new feature (only signature upload exists today), not implemented in this pass
Bg_21 | User | Try to add user when user has only access of user section | User should be on the user section Add role permission are not listed | 1. Click on add user button 2. Enter the Mail and password 3. Select role 4. And click on submit button |  | User should be add successfull | Role list is not displaying Usrer not added | FAIL | High | High | https://drive.google.com/file/d/104FscA9cN9dQE_5b6vXjSvbYs9xiSNKt/view?usp=drive_link | Here User add failed due to user has no access for role section System should display the name in the selection list of the unaccess section detail Because in many section same problem is coming | Resolved — Role list now readable by users.create/edit (via requireAnyPermission), fixing the User form's empty Role dropdown
Bg_22 | Role & Permiossion | Check View permission auto check for module if user allow access of add/edit or delete permission | User should be on the Role section Roles are already added | 1. Click on the add role 2. Click onthe edit/delete/create labeled check box of the module 3. Check is the View section auto checked or not |  | View section Get auto checked if user gave add/edit/delete permission to the module | View section is not checked automatically And user unable to access that module | FAIL | Medium | High | https://drive.google.com/file/d/1PJeT0O282axd9LhoubxysvrqaDneGtHR/view?usp=drive_link | See if the user check the edit or other checkbox than there view checkbox should be auto checked | Resolved — Checking Create/Edit/Delete for a module now auto-checks that module's View permission (and unchecking View clears the others), preventing this misconfiguration
Bg_23 | [12 empty] | N/A — Empty placeholder row, no test case content