## Sheet1
Testcase Id | Module Name | Test Casse | Pre Condition | Step to Execute | Test Data | Expected Result | Actual Result |  | Priority | Severity | Files | Remark | Resolved or Not
Bg_23 | Bill Settlement | Verify Money deducted from bill amount if user advance paid | Client already paid bill/clinet paid by advanced instead of bill payment | 1. Create an Invoice to that client that already paid an advance amount 2. Now check the amount is deducted from that amount or not 3. Verify in the client ledger 4. Check the invoice status of the following bill |  | Bill status should be display as change to paid or partial paid according to the amount in the bill and Client's account And the ledger would be adjust and properly calculate and display the pending and excess amount in it | Here Client's ledger is adjust properly and display the correct aqmount But the Invoice Status display as Unpaid while client has already paid in advance | FAIL | High | High | https://drive.google.com/file/d/1YVRAfMW4I-_AEV_950dov05_ejehTksQ/view?usp=sharing | Here if the Client doing paymnet in advance than it should be adjusted in the invoice that first created and the status of Invoice should be adjust like that Ex: If user paid 10000 advance and B1 and B2 bill unpaid than syustem should be Adjust that amoiunt in B1 first and If amount Exceed than adjust it to B2 and If it not enough for both than B1 will partial paid and B2 will unpaid. like that. | Resolved — Advance payments now settle the client's unpaid credit invoices automatically, oldest-first (fills B1 fully, spills the remainder into B2, etc.). Runs on payment add/edit/delete and invoice create/edit/delete; cash invoices are left untouched. Verified: 10,000 advance → 6,000 invoice Paid, 7,000 invoice Partial (4,000), next Unpaid; reverses correctly if the payment is deleted.
Bg_24 | Confirmation popup | Verify Confirmation Message popup | User should be on the invoice Manger | 1. Clcik on Add Invoice and Fill up all detail and Create it 2. Check confirmation message display or not 3. Try to delete that invice and check is Delete confirmaton message display or not 4. Do the same thing in all module and verify it |  | Successfully Added/ updated/ Deleted/ Deactivated Message should display on the screen when user do any Action | Here No message display when user do the following action anywhere in the all website | FAIL | low | low | https://drive.google.com/file/d/18oxEvkzvnnFvmrBUivb_SnZzwJRGM1Ty/view?usp=drive_link | Confirmation message display on Add, Edit, Delete, Deactivate Actions in In Invoice, Client, Groups, Payment, Setting, Role & Permission and User. | Resolved — Success messages now shown for Add/Edit/Delete/Deactivate across Invoices, Clients, Groups, Payments, Roles and Users (Settings already had one).
Bg_25 | User | Verify zero assign permission Role are displaying on User's Add/edit section | User should be on user section a Role should already added who has zero access | 1. Click on Add button fill all data valid credential 2. Click on Role dropdown list 3. Check is the zero permission assigned role display there or not |  | If role has zero assigned permission than it should not displayed on the user side | Zero permission assigned role also display there | FAIL | low | low | https://drive.google.com/file/d/18z2O1CRKGdzfBXdfuXmu2RSCFssXdHQu/view?usp=drive_link |  | Resolved — Roles with zero assigned permissions are no longer offered in the Add/Edit User role dropdown (super_admin and the user's currently-assigned role remain listed).
Bg_26 | User | Check the User name field is mandatory or not and What is displaying on the User Info Panel | User should be at user section. | 1. Click on Create user and try to add user with out filling data in User name field 2. Click on Edit button And make username field empty and try to update user 3. Check outcome 4. Check User Info Panel by what name is it displayed there |  | Username Should be mandatory field in Create User section In User Info Panel User name should be display instead of mail it look good | In User Info Panel ther Email is displayed Instead of user System kept username as optional field instead of madatory | Improvement | low | low | https://drive.google.com/file/d/1Sv70KxY9IlJsisOaMb0kvsXcNOT-GwwW/view?usp=sharing |  | Resolved — Name is now a required field on user create/edit (client and server side), and the sidebar user panel shows the name instead of the email (email kept as tooltip; falls back to email for older accounts with no name).
Bg_27 | Invoice | Verify Payment button if user had not permission of payment | User should be on the Invoice section. Unpaid invoice already there in invoice list user has not permission of doing payment | 1. Try to locate Payment button 2. Click on it and FIll the detail and click submit button 3. See the output |  | System should not display the payment button If user has not permission of mange payment | Payment button displayed but system did not allow user to add payment in it | FAIL | medium | medium | https://drive.google.com/file/d/144-8zhuX1epIDs0cmrKV32hMTW04H5a5/view?usp=drive_link | Payment button only display in Invoice when user has permission of add payment | Resolved — The + Payment button is now hidden wherever the user lacks the 'payments.create' permission (Invoices list, Clients list, Dashboard overdue panel and Ledger page).
Bg_28 | Invoice | Try to add taxes and discount on the invoice AMT | User should be on add Invoice section | 1. Fill all data in invoice form with valid data 2. Now try to add the tax and discount on the total Amount of the invoice 3. Also Check the roundoff option also is the amount got roundoff or not if came in decimal |  | System allow user to apply tax and discount on the invoice And also roundoff can done | Here there is not feature for taxes and discount | Need for Confiramtion | High | High | https://drive.google.com/file/d/1MqA_pVKiDGj8OTdVL-6uZNB8jhCB9_fI/view?usp=drive_link | As this product is used in india so Tax and discount section should be present here And for that it should be manged from the Setting section and Apply from Invoice and Should display Properly in the Bill and PDF | Not Implemented — Needs Product Confirmation. Tax/discount/round-off is a new feature affecting invoice money calculations and the PDF layout, and needs decisions first (GST type & rates, per-line vs per-invoice, % vs flat discount, round-off rule, and how existing invoices are treated). Flagged to the developer/client for sign-off before building.